## Sheet1
Task ID | Task Name | Start Date | End Date | Duration | Percent Complete | Dependencies
Research | Find sources | 2015-01-01 | 2015-01-05 |  | 100
Write | Write Paper | 2015-01-06 | 2015-01-09 |  | 25 | Research,Outline
Cite | Create Bibliography | 2015-01-06 | 2015-01-07 |  | 20 | Research
Complete | Hand in paper | 2015-01-09 | 2015-01-10 |  | 0 | Cite,Write
Outline | Outline paper | 2015-01-05 | 2015-01-06 |  | 100 | Research
3
1
1
1